## AC Target loads
Process 1 - Target loads
Introduction -
Process ABP: DE.AO.02.03.04 Perform loads calculation & analysis
Deliverable name ABP: Internal Aircraft Loads Status Dossier
/
“Convergence Levels” and its impact on on “Lead time” & “FTE”. The objective is to achieve critical path for the lead time and FTEs based on convergence levels
Convergence Levels | CL0 (preliminary) | CL1 (defined) | CL2 (matured) | CL3 (finalised) | Comments
Full scope Lead Time (weeks) | 3 | 4 | 5 | 6 | NOMINAL lead time
Full scope FTE | 2 | 3 | 5 | 5 | NOMINAL FTE
“Complexity” and its impact on “Lead time” & “FTE”
Complexity | Minimum scope (one system, one zone, one ATA, MINOR…) | 25% scope | 50% scope | 75% scope | 100% Full scope (all systems, all zones, all ATA, CATASTROPHIC …) | Comments
Lead time (Weeks) | 2 | 3 | 4 | 5 | 6 | NOMINAL lead time
FTE | 1 | 2 | 3 | 4 | 5 | NOMINAL FTE
“FTE” and its impact on “Cost”
Comments
FTE Cost | 1 | 3 | 5 | 10 | 50 | 100 | Nominal FTE
Toolset fix cost (k$) | 100 | 100 | 100 | 100 | 200 | 200
Toolset license cost (k$) | 1 | 5 | 10 | 10 | 40 | 50
People training cost (k$) | 50 | 50 | 50 | 50 | 50 | 100
Total cost (k$) | 151 | 155 | 160 | 160 | 290 | 350 | Nominal cost
“FTE” and its impact on “Lead time” evolutions
Process FTE | LEAD TIME evolution (week) | Comment
0.5 x Nominal FTE | 10
0.75 x Nominal FTE | 8
Required Nominal FTE (for full scope) | 6 | NOMINAL lead time
1.5 x Nominal FTE | 6
2 x Nominal FTE | 5
3 x Nominal FTE | 5

## MGY
Process 2 - Master Geometry
Introduction
Process ABP: DE.PA.01.04.03 Deliverable name ABP: Release Aircraft Master Geometry and Preliminary Space Allocation Mock-Up / Master Geometry
“Convergence Levels” and its impact on on “Lead time” & “FTE”. The objective is to achieve critical path for the lead time and FTEs based on convergence levels
Convergence Levels | CL0 (preliminary) | CL1 (defined) | CL2 (matured) | CL3 (finalised) | Comments
Full scope Lead Time (weeks) | 1 | 2 | 3 | 3 | NOMINAL lead time
Full scope FTE | 1 | 2 | 2 | 3 | NOMINAL FTE
“Complexity” and its impact on “Lead time” & “FTE”
Complexity | Minimum scope (one system, one zone, one ATA, MINOR…) | 25% scope | 50% scope | 75% scope | 100% Full scope (all systems, all zones, all ATA, CATASTROPHIC …) | Comments
Lead time (weeks) | 1 | 2 | 2 | 3 | 3 | NOMINAL lead time
FTE | 2 | 2 | 3 | 3 | 3 | NOMINAL FTE
“FTE” and its impact on “Cost”
Comments
FTE Cost | 1 | 2 | 3 | 10 | 50 | 100 | Nominal FTE
Toolset fix cost (k$) | 100 | 100 | 100 | 100 | 100 | 100
Toolset license cost (k$) | 1 | 2 | 3 | 10 | 50 | 100
People training cost (k$) | 20 | 20 | 20 | 20 | 20 | 50
Total cost (k$) | 121 | 122 | 123 | 130 | 170 | 250 | Nominal cost
“FTE” and its impact on “Lead time” evolutions
Process FTE | LEAD TIME evolution (week) | Comment
0.5 x Nominal FTE | 5
0.75 x Nominal FTE | 4
Required Nominal FTE (for full scope) | 3 | NOMINAL lead time
1.5 x Nominal FTE | 3
2 x Nominal FTE | 3
3 x Nominal FTE | 2

## GFEM
Process 3 - Global Finite Element Model
Introduction
Process ABP: DE.PA.03.02.06 Perform Global Finite Element Model Analysis Deliverable name ABP: Component Global Finite Element Model
“Convergence Levels” and its impact on on “Lead time” & “FTE”. The objective is to achieve critical path for the lead time and FTEs based on convergence levels
Convergence Levels | CL0 (preliminary) | CL1 (defined) | CL2 (matured) | CL3 (finalised) | Comments
Full scope Lead Time (weeks) | 4 | 5 | 8 | 11 | NOMINAL lead time
Full scope FTE | 2 | 3 | 5 | 10 | NOMINAL FTE
“Complexity” and its impact on “Lead time” & “FTE”
Complexity | Minimum scope (one system, one zone, one ATA, MINOR…) | 25% scope | 50% scope | 75% scope | 100% Full scope (all systems, all zones, all ATA, CATASTROPHIC …) | Comments
Lead time (weeks) | 4 | 5 | 6 | 8 | 11 | NOMINAL lead time
FTE | 2 | 4 | 6 | 8 | 10 | NOMINAL FTE
“FTE” and its impact on “Cost”
Comments
FTE Cost | 1 | 5 | 10 | 20 | 50 | 100 | Nominal FTE
Toolset fix cost (k$) | 100 | 100 | 100 | 100 | 100 | 100
Toolset license cost (k$) | 50 | 50 | 50 | 50 | 100 | 100
People training cost (k$) | 30 | 30 | 30 | 30 | 50 | 50
Total cost (k$) | 180 | 180 | 180 | 180 | 250 | 250 | Nominal cost
“FTE” and its impact on “Lead time” evolutions
Process FTE | LEAD TIME evolution (week) | Comment
0.5 x Nominal FTE | 15
0.75 x Nominal FTE | 12
Required Nominal FTE (for full scope) | 11 | NOMINAL lead time
1.5 x Nominal FTE | 10
2 x Nominal FTE | 8
3 x Nominal FTE | 7

## Sizing check
Process 4 - Sizing Check
Introduction
Process ABP: DE.PA.03.01.08 Integrate Structure, Systems and Cabin Installation within Digital Mock-Up Deliverable name ABP: Structure analysis report
“Convergence Levels” and its impact on on “Lead time” & “FTE”. The objective is to achieve critical path for the lead time and FTEs based on convergence levels
Convergence Levels | CL0 (preliminary) | CL1 (defined) | CL2 (matured) | CL3 (finalised) | Comments
Full scope Lead Time (weeks) | 5 | 6 | 8 | 9 | NOMINAL lead time
Full scope FTE | 2 | 2 | 3 | 3 | NOMINAL FTE
“Complexity” and its impact on “Lead time” & “FTE”
Complexity | Minimum scope (one system, one zone, one ATA, MINOR…) | 25% scope | 50% scope | 75% scope | 100% Full scope (all systems, all zones, all ATA, CATASTROPHIC …) | Comments
Lead time (weeks) | 3 | 5 | 7 | 8 | 9 | NOMINAL lead time
FTE | 1 | 2 | 2 | 3 | 3 | NOMINAL FTE
“FTE” and its impact on “Cost”
Comments
FTE Cost | 1 | 2 | 3 | 10 | 50 | 100 | Nominal FTE
Toolset fix cost (k$) | 500 | 500 | 500 | 500 | 500 | 500
Toolset license cost (k$) | 10 | 20 | 20 | 50 | 100 | 200
People training cost (k$) | 25 | 25 | 25 | 25 | 25 | 25
Total cost (k$) | 575 | 545 | 545 | 575 | 625 | 725 | Nominal cost
“FTE” and its impact on “Lead time” evolutions
Process FTE | LEAD TIME evolution (week) | Comment
0.5 x Nominal FTE | 12
0.75 x Nominal FTE | 10
Required Nominal FTE (for full scope) | 9 | NOMINAL lead time
1.5 x Nominal FTE | 9
2 x Nominal FTE | 8
3 x Nominal FTE | 7

## Aero-load-stress value stream
Process 5
Convergence Levels | CL0 (preliminary) | CL1 (defined) | CL2 (matured) | CL3 (finalised) | Comments
Full scope Lead Time (weeks) | 15 | 25 | 45 | 45 | NOMINAL lead time
Full scope FTE | 5 | 20 | 25 | 30 | NOMINAL FTE
Complexity | Minimum scope (one system, one zone, one ATA, MINOR…) | 25% scope | 50% scope | 75% scope | 100% Full scope (all systems, all zones, all ATA, CATASTROPHIC …) | Comments
Lead time | 25 | 30 | 35 | 40 | 45 | NOMINAL lead time
FTE | 20 | 22 | 25 | 27 | 30 | NOMINAL FTE
Comments
FTE Cost | 1 | 2 | 30 | 10 | 50 | 100 | Nominal FTE
Toolset fix cost (k$) | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
Toolset license cost (k$) | 100 | 200 | 200 | 500 | 500 | 500
People training cost | 100 | 100 | 100 | 100 | 100 | 100
Total cost (k$) | 5200 | 5300 | 5300 | 5600 | 5600 | 5600 | Nominal cost
Process FTE | LEAD TIME evolution (week) | Comment
0.5 x Nominal FTE | 55
0.75 x Nominal FTE | 50
Required Nominal FTE (for full scope) | 45 | NOMINAL lead time
1.5 x Nominal FTE | 40
2 x Nominal FTE | 35
3 x Nominal FTE | 30

## Feuil1
Process 5 - Aero-load-stress value stream
Introduction
Process ABP: DE.PA.03.01.08 Integrate Structure, Systems and Cabin Installation within Digital Mock-Up Deliverable name ABP: Structure analysis report
“Convergence Levels” and its impact on on “Lead time” & “FTE”. The objective is to achieve critical path for the lead time and FTEs based on convergence levels
Convergence Levels | CL0 (preliminary) | CL1 (defined) | CL2 (matured) | CL3 (finalised) | Comments
Full scope Lead Time (weeks) | 15 | 25 | 45 | 45 | NOMINAL lead time
Full scope FTE | 5 | 20 | 25 | 30 | NOMINAL FTE
“Complexity” and its impact on “Lead time” & “FTE”
Complexity | Minimum scope (one system, one zone, one ATA, MINOR…) | 25% scope | 50% scope | 75% scope | 100% Full scope (all systems, all zones, all ATA, CATASTROPHIC …) | Comments
Lead time (weeks) | 25 | 30 | 35 | 40 | 45 | NOMINAL lead time
FTE | 20 | 22 | 25 | 27 | 40 | NOMINAL FTE
“FTE” and its impact on “Cost”
Comments
FTE Cost | 1 | 2 | 3 | 10 | 50 | 100 | Nominal FTE
Toolset fix cost (k$) | 5000 | 5000 | 500 | 500 | 500 | 500
Toolset license cost (k$) | 100 | 200 | 20 | 50 | 100 | 200
People training cost (k$) | 100 | 100 | 25 | 25 | 25 | 25
Total cost (k$) | 5200 | 5300 | 545 | 575 | 625 | 725 | Nominal cost
“FTE” and its impact on “Lead time” evolutions
Process FTE | LEAD TIME evolution (week) | Comment
0.5 x Nominal FTE | 12
0.75 x Nominal FTE | 10
Required Nominal FTE (for full scope) | 9 | NOMINAL lead time
1.5 x Nominal FTE | 9
2 x Nominal FTE | 8
3 x Nominal FTE | 7